## Sheet1
MV CABLE LAYING |  |  | RFI CODE
ITP NO. | EGY2001-G000-___-&EQA-00001
MOS | EGY2001-G000-___-&EDC-00001
ICL | EGY2001-G000-___-&EDC-00004
ACTIVITY | ITP POINT | Discription
Excavation | 6.1 | Check Trench Excavation as per drawing | EGY2001-MV-EL-EX-RFI-0000x
Sand Bed + Cable Laying | 5 / 6.2 | Sand Bedding with Cable Laying & dressing | EGY2001-MV-EL-CL-RFI-0000x
Sand Cover + Earthing | 6.3 | Sand Cover with Earthing Conductor Laying | EGY2001-MV-EL-SC-RFI-0000x
First Backfill + Warning Tape | 6.4 | First Backfill With Warning Tape | EGY2001-MV-EL-BF-RFI-0000x
Final Backfill | 6.5 | Final Backfill | EGY2001-MV-EL-BF-RFI-0000x
ACTIVITY | ITP POINT | Discription
Excavation (Road crossing) | 7.1 | Check Trench Excavation as per drawing | EGY2001-MV-EL-RC-RFI-0000x
HDPE Pipes | 7.2 | Check material for HDPE pipes and dimensions | EGY2001-MV-EL-RC-RFI-0000x
Concrete | 7.3 | Check the dimension for concrete | EGY2001-MV-EL-RC-RFI-0000x
First Backfill + Warning Tape (Road crossing) | 7.4 | First Backfill With Warning Tape | EGY2001-MV-EL-RC-RFI-0000x
Final Backfill (Road crossing) | 7.5 | Final Backfill | EGY2001-MV-EL-RC-RFI-0000x
ACTIVITY | ITP POINT | Discription
Jointing | 8 | MV & FO Cable Jointing Works | EGY2001-MV-EL-JO-RFI-0000x
Termination | 8 | MV & FO Cable Termination Works | EGY2001-MV-EL-TR-RFI-0000x